## app4
Appendix 4
GANTT CHART SHOWING IMPLEMENTATION PLAN AND STATUS REPORT
PERIOD ENDING (Weeks)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
ACTIVITY
Hardware Acquisition:
Obtain Quotations
Examine Quotations/Make Award |  |  | :::::
Place Orders |  |  | :::::
Await Arrival
Clear equipment from customs | [7 empty] | :::::
Examine equipment for compliance | [7 empty] | :::::
Software acquisition
Installation and Testing | [9 empty] | :::::
Personnel Training:
Customer Service Rep. Training | [9 empty] | :::::
Accounts Clerk Training
Management Training / Orientation | [11 empty] | :::::
Export Microsoft Access 2000 Data | [11 empty] | :::::
Import Data Into SQL Server 2000 | [11 empty] | :::::
Pilot Test
Changeover | [23 empty] | :::::
N.B. These activities take days | :::::

## app4#2
IMPLEMENTATION PLAN AND STATUS REPORT
NUMBER OF DAYS
ACTIVITY | 1 | 2 | 3 | 4 | 5
Examine Quotations/Make Award
Place Orders
Clear equipment from customs
Examine equipment for compliance
Installation and Testing
Customer Service Rep Training
Accounts Clerk Training
Management Orientation/Training
Export Microsoft Access 2000 data
Import Access data into SQL Server 2000
Changeover